## Dashboard
A.B.C.D.E — Backend & Integration Progress
Cardiac demo · 10-day plan · update Status columns in the other sheets — everything here recalculates. Team: Mohamed, Tasnem (backend+demo video), Mena, Heba (mobile), Sara (dashboards), Mayar (UI/UX, data collection & content).
10-Day Plan tasks
| Total | Done | In Progress | Blocked | % Done
| 35 | 0 | 0 | 0 | 0%
API endpoints (99 — Postman 65 + 34 new/expanded)
| Total | Done | In Progress | Blocked | % Done
| 99 | 0 | 0 | 0 | 0%
Mobile screens wired
| Total | Done | In Progress | Blocked | % Done
| 16 | 0 | 0 | 0 | 0%
Dashboard routes wired
| Total | Done | In Progress | Blocked | % Done
| 41 | 0 | 0 | 0 | 0%
Per person — Done / Owned
Member | Plan tasks | API endpoints | Mobile screens | Dashboard routes | Overall % done
Mohamed | 0 / 13 | 0 / 59 | 0 / 0 | 0 / 0 | 0%
Tasnem | 0 / 15 | 0 / 40 | 0 / 0 | 0 / 0 | 0%
Mena | 0 / 0 | 0 / 0 | 0 / 8 | 0 / 0 | 0%
Heba | 0 / 0 | 0 / 0 | 0 / 8 | 0 / 0 | 0%
Sara | 0 / 0 | 0 / 0 | 0 / 0 | 0 / 41 | 0%
Mayar | 0 / 7 | — | — | — | 0%
API endpoints by due day
Day | Due | Done | % Done
Day 2 | 20 | 0 | 0%
Day 3 | 11 | 0 | 0%
Day 4 | 14 | 0 | 0%
Day 5 | 15 | 0 | 0%
Day 6 | 19 | 0 | 0%
Day 7 | 6 | 0 | 0%
Day 8 | 9 | 0 | 0%
Day 9 | 5 | 0 | 0%

## Plan_10Days
Day | Date | Owner | Service | Task | Deliverable / Definition of Done | Weight | Status | Notes
1 | Thu 11/6 | Mohamed | Core | Laravel 11 scaffold + repo + CI | Repo builds; pipeline green | 2 | Not Started
1 | Thu 11/6 | Mohamed | S1 | Sanctum auth + RBAC middleware (8 roles) | Login returns role token; middleware blocks wrong role | 3 | Not Started
1 | Thu 11/6 | Mohamed | S12 | Audit observer + 15-min edit-window trait | Every write logged in audit_logs | 2 | Not Started
1 | Thu 11/6 | Tasnem | Core | All migrations (38 tables) + models + factories | php artisan migrate clean on fresh DB | 3 | Not Started
1 | Thu 11/6 | Tasnem | Core | Seeder reproducing data.js demo dataset | 6 patients incl. ALM-20413; depts; staff; education | 3 | Not Started
1 | Thu 11/6 | Mayar | DATA | Send the 4 data-request workbooks to the hospital + brief their contact person | Hospital confirms receipt and a return date (≤ Day 4) | 2 | Not Started
2 | Fri 12/6 | Mohamed | S1 | Identity endpoints #1–11 (login, QR, register, cards, search, prefs, accessibility) | All S1 endpoints pass feature tests | 3 | Not Started
2 | Fri 12/6 | Tasnem | S2 | Public portal #12–15 + appointments CRUD #16–20 | Landing + mobile appointments can run on real API | 3 | Not Started
2 | Fri 12/6 | Mayar | UIUX | Design system & brand assets shared by mobile + dashboards | Tokens/components file delivered to Mena, Heba, Sara | 2 | Not Started
3 | Sat 13/6 | Mohamed | S3 | Visits open/get/list + triage + advance + timeline (#23–27) | UC-1 arrival→triage→advance works via API | 3 | Not Started
3 | Sat 13/6 | Mohamed | S7 | Stage-change → notification event | Stage move creates notification rows | 1 | Not Started
3 | Sat 13/6 | Tasnem | S4 | Vitals + NEWS2 engine + risk endpoints (#37–42) | Vitals write computes NEWS2; ≥5 fires alert event | 3 | Not Started
4 | Sun 14/6 | Mohamed | S3 | Clinical gates: consents, checklists, RSTP, cath-type, care-plan, committee (#28–36) | Committee authorize produces Direct Admission Form no. | 3 | Not Started
4 | Sun 14/6 | Tasnem | S5 | Medication: prescriptions, MAR administer, reconciliation, pharmacy (#43–47) | Nurse MAR + patient adherence both write administrations | 3 | Not Started
4 | Sun 14/6 | Mayar | DATA | Collect & clean File 1 (hospital master) + File 2 (patients/visits) from hospital | Seeder-ready JSON/CSV handed to Tasnem | 3 | Not Started
5 | Mon 15/6 | Mohamed | S7 | Emergency: SOS, chain answer/advance, code-blue, board, metrics, notifications (#61–68) | Escalation advances on no-answer; board lists active | 3 | Not Started
5 | Mon 15/6 | Tasnem | S5 | Diagnostics: orders, results+flags, diagnosis ICD, patient file, consultations (#48–54) | P0 COMPLETE — doctor file & results live | 3 | Not Started
5 | Mon 15/6 | Mayar | DATA | Collect & clean File 3 (clinical cardiac) — verify values with a clinician | Cardiac case data validated; handed to Tasnem | 3 | Not Started
6 | Tue 16/6 | Mohamed | S10 | Feedback +20pts, complaints + 6h SLA, list/respond/escalate, dashboard (#79–84) | SLA breach flag computed; quality dashboard aggregates | 3 | Not Started
6 | Tue 16/6 | Tasnem | S8 | Family link/accept/permissions + BR-3 filtered resource (#69–73) | Tests prove family never receives file/results fields | 3 | Not Started
6 | Tue 16/6 | Tasnem | S9 | Billing: insurance, committee memo, financial file, payments (#74–78) | 4-outcome insurance read; payment returns receipt | 2 | Not Started
6 | Tue 16/6 | Tasnem | S11 | Education videos/relax + care-points ledger (#85–87) | Stage-matched content; points balance correct | 1 | Not Started
6 | Tue 16/6 | Mayar | CONTENT | Education videos/news/relax content + AR/EN/RU translations of UI strings | Content seeded; 3-language strings file delivered | 3 | Not Started
7 | Wed 17/6 | Mohamed | S6 | AI: advisor+triage (RAG, red-flag→S7), drafts+approve, transcribe, translate (#55–60) | Draft saved to record ONLY after approve (NFR-2 test) | 3 | Not Started
7 | Wed 17/6 | Tasnem | INT | Integration day 1 with Heba — wire mobile P0 screens | Mobile login→journey→vitals→SOS on real API; CONTRACT FREEZE | 3 | Not Started
8 | Thu 18/6 | Mohamed | S12 | Admin: users/roles/permissions, audit query, integrations, ai-models, KPIs, reports (#88–91) | Director KPIs + admin screens servable | 3 | Not Started
8 | Thu 18/6 | Tasnem | INT | Integration day 2 with Heba — wire dashboards P0 (Sara consumes) | Reception/nurse/doctor/emergency dashboards on real API | 3 | Not Started
8 | Thu 18/6 | Mayar | DATA | Collect & clean File 4 (operational/quality) + demo storyboard | KPI/feedback data seeded; demo script approved by team | 2 | Not Started
9 | Fri 19/6 | Mohamed | S2 | Appointment status/assign (#21–22) + nav map/search/route | P2 endpoints green | 2 | Not Started
9 | Fri 19/6 | Tasnem | QA | Hardening: RBAC+BR-3 sweep, edit window, rate limits, N+1, seeder polish | All 91 endpoints green in Postman runner | 3 | Not Started
9 | Fri 19/6 | Tasnem | DEMO | Demo video — record UC-1 cardiac flow (mobile + dashboards), edit + voiceover | Draft video shared with team for review | 2 | Not Started
10 | Sat 20/6 | Mohamed | OPS | Deploy API (host, .env, HTTPS) + E2E of UC-1…UC-6 | Demo environment live | 3 | Not Started
10 | Sat 20/6 | Tasnem | OPS | Demo data freeze, tag v1.0-demo, handover doc | Team can run the full cardiac demo unaided | 2 | Not Started
10 | Sat 20/6 | Tasnem | DEMO | Final demo video render + backup recording of live demo path | Final video delivered; plays at presentation | 2 | Not Started
10 | Sat 20/6 | Mayar | CONTENT | Demo polish: landing/public pages deploy + presentation visuals | Landing live; slides/visuals ready | 2 | Not Started

## API_Endpoints
# | Source | Method | Path | Service | Owner | Due Day | Min. Role | Status | Tested in Postman | Notes
1 | P | POST | /auth/login | S1 | Mohamed | 2 | public | Not Started | No
2 | P | POST | /auth/login/qr | S1 | Mohamed | 2 | public | Not Started | No
3 | P | POST | /auth/logout | S1 | Mohamed | 2 | any | Not Started | No
4 | P | POST | /patients/register | S1 | Mohamed | 2 | public/reception | Not Started | No
5 | P | GET | /patients/{serial} | S1 | Mohamed | 2 | owner/staff | Not Started | No
6 | + | GET | /patients?q= | S1 | Mohamed | 2 | staff | Not Started | No
7 | P | PUT | /patients/{serial}/preferences | S1 | Mohamed | 2 | owner | Not Started | No
8 | P | POST | /patients/{serial}/cards | S1 | Mohamed | 2 | reception | Not Started | No
9 | + | POST | /patients/{serial}/qr | S1 | Mohamed | 2 | reception | Not Started | No
10 | P | GET | /patients/{serial}/accessibility | S1 | Mohamed | 2 | owner | Not Started | No
11 | P | PUT | /patients/{serial}/accessibility | S1 | Mohamed | 2 | owner | Not Started | No
12 | P | GET | /public/hospital | S2 | Tasnem | 2 | public | Not Started | No
13 | P | GET | /public/departments | S2 | Tasnem | 2 | public | Not Started | No
14 | P | GET | /public/doctors | S2 | Tasnem | 2 | public | Not Started | No
15 | P | GET | /public/news | S2 | Tasnem | 2 | public | Not Started | No
16 | P | POST | /appointments | S2 | Tasnem | 2 | public/patient | Not Started | No
17 | P | GET | /appointments | S2 | Tasnem | 2 | patient/staff | Not Started | No
18 | P | GET | /appointments/slots | S2 | Tasnem | 2 | public | Not Started | No
19 | P | PATCH | /appointments/{id}/reschedule | S2 | Tasnem | 2 | owner | Not Started | No
20 | P | DELETE | /appointments/{id} | S2 | Tasnem | 2 | owner | Not Started | No
21 | + | PATCH | /appointments/{id}/status | S2 | Mohamed | 9 | reception | Not Started | No
22 | + | POST | /appointments/{id}/assign | S2 | Mohamed | 9 | reception/director | Not Started | No
23 | P | POST | /visits | S3 | Mohamed | 3 | reception | Not Started | No
24 | P | GET | /visits/{id} | S3 | Mohamed | 3 | role-filtered | Not Started | No
25 | + | GET | /visits?filters | S3 | Mohamed | 3 | staff | Not Started | No
26 | P | POST | /visits/{id}/triage | S3 | Mohamed | 3 | nurse | Not Started | No
27 | P | POST | /visits/{id}/advance | S3 | Mohamed | 3 | doctor/nurse | Not Started | No
28 | + | POST | /visits/{id}/cath-type | S3 | Mohamed | 4 | doctor | Not Started | No
29 | + | POST | /visits/{id}/consents | S3 | Mohamed | 4 | doctor | Not Started | No
30 | + | POST | /consents/{id}/respond | S3 | Mohamed | 4 | patient/family | Not Started | No
31 | + | POST | /visits/{id}/checklists | S3 | Mohamed | 4 | nurse | Not Started | No
32 | + | POST | /visits/{id}/transport | S3 | Mohamed | 4 | nurse | Not Started | No
33 | + | POST | /visits/{id}/committee | S3 | Mohamed | 4 | doctor/reception | Not Started | No
34 | + | POST | /committee/{id}/authorize | S3 | Mohamed | 4 | committee | Not Started | No
35 | + | POST | /visits/{id}/care-plan | S3 | Mohamed | 4 | doctor | Not Started | No
36 | + | GET | /visits/{id}/care-plan | S3 | Mohamed | 4 | doctor/nurse | Not Started | No
37 | P | POST | /visits/{id}/vitals | S4 | Tasnem | 3 | nurse | Not Started | No
38 | P | GET | /visits/{id}/vitals | S4 | Tasnem | 3 | staff/owner | Not Started | No
39 | P | GET | /visits/{id}/risk-score | S4 | Tasnem | 3 | staff | Not Started | No
40 | P | POST | /visits/{id}/risk-score/recompute | S4 | Tasnem | 3 | doctor | Not Started | No
41 | + | POST | /visits/{id}/vte | S4 | Tasnem | 3 | doctor | Not Started | No
42 | + | PUT | /visits/{id}/thresholds | S4 | Tasnem | 3 | doctor | Not Started | No
43 | P | POST | /visits/{id}/prescriptions | S5 | Tasnem | 4 | doctor | Not Started | No
44 | P | GET | /visits/{id}/prescriptions | S5 | Tasnem | 4 | staff/owner | Not Started | No
45 | P | POST | /prescriptions/{id}/administer | S5 | Tasnem | 4 | nurse/patient | Not Started | No
46 | + | POST | /visits/{id}/reconciliation | S5 | Tasnem | 4 | doctor/nurse | Not Started | No
47 | P | GET | /pharmacy/availability | S5 | Tasnem | 4 | staff | Not Started | No
48 | P | POST | /visits/{id}/orders | S5 | Tasnem | 5 | doctor | Not Started | No
49 | P | GET | /visits/{id}/orders | S5 | Tasnem | 5 | staff | Not Started | No
50 | P | GET | /visits/{id}/results | S5 | Tasnem | 5 | doctor/owner | Not Started | No
51 | + | POST | /orders/{id}/result | S5 | Tasnem | 5 | doctor/lab | Not Started | No
52 | + | POST | /visits/{id}/diagnosis | S5 | Tasnem | 5 | doctor | Not Started | No
53 | P | GET | /patients/{serial}/file | S5 | Tasnem | 5 | doctor/owner | Not Started | No
54 | P | POST | /visits/{id}/consultations | S5 | Tasnem | 5 | doctor | Not Started | No
55 | P | POST | /assistant/ask | S6 | Mohamed | 7 | patient/family | Not Started | No
56 | P | POST | /assistant/triage | S6 | Mohamed | 7 | patient | Not Started | No
57 | P | POST | /documentation/draft | S6 | Mohamed | 7 | doctor | Not Started | No
58 | P | POST | /documentation/{draftId}/approve | S6 | Mohamed | 7 | doctor | Not Started | No
59 | P | POST | /documentation/transcribe | S6 | Mohamed | 7 | doctor | Not Started | No
60 | P | POST | /documentation/translate | S6 | Mohamed | 7 | staff/patient | Not Started | No
61 | P | POST | /emergency/sos | S7 | Mohamed | 5 | patient/family | Not Started | No
62 | + | GET | /emergency/active | S7 | Mohamed | 5 | emergency/nurse | Not Started | No
63 | + | POST | /emergency/{id}/answer | S7 | Mohamed | 5 | emergency | Not Started | No
64 | + | POST | /emergency/{id}/advance | S7 | Mohamed | 5 | emergency/system | Not Started | No
65 | + | POST | /emergency/code-blue | S7 | Mohamed | 5 | nurse/emergency | Not Started | No
66 | + | GET | /emergency/metrics | S7 | Mohamed | 5 | emergency/director | Not Started | No
67 | P | GET | /notifications | S7 | Mohamed | 5 | any | Not Started | No
68 | P | POST | /notifications/{id}/read | S7 | Mohamed | 5 | owner | Not Started | No
69 | P | POST | /patients/{serial}/family | S8 | Tasnem | 6 | patient | Not Started | No
70 | P | GET | /patients/{serial}/family | S8 | Tasnem | 6 | patient/family | Not Started | No
71 | + | POST | /family/{id}/accept | S8 | Tasnem | 6 | family | Not Started | No
72 | P | PATCH | /family/{id}/permissions | S8 | Tasnem | 6 | patient | Not Started | No
73 | P | DELETE | /family/{id} | S8 | Tasnem | 6 | patient | Not Started | No
74 | P | GET | /patients/{serial}/insurance | S9 | Tasnem | 6 | reception/owner | Not Started | No
75 | + | PATCH | /patients/{serial}/insurance | S9 | Tasnem | 6 | reception | Not Started | No
76 | P | POST | /visits/{id}/billing/committee-review | S9 | Tasnem | 6 | reception | Not Started | No
77 | P | GET | /visits/{id}/financial-file | S9 | Tasnem | 6 | reception/owner | Not Started | No
78 | P | POST | /visits/{id}/payments | S9 | Tasnem | 6 | patient/reception | Not Started | No
79 | P | POST | /stages/{id}/feedback | S10 | Mohamed | 6 | patient/family | Not Started | No
80 | P | POST | /complaints | S10 | Mohamed | 6 | patient | Not Started | No
81 | + | GET | /complaints | S10 | Mohamed | 6 | quality | Not Started | No
82 | + | PATCH | /complaints/{id} | S10 | Mohamed | 6 | quality | Not Started | No
83 | + | GET | /feedback | S10 | Mohamed | 6 | quality | Not Started | No
84 | P | GET | /quality/dashboard | S10 | Mohamed | 6 | quality/director | Not Started | No
85 | P | GET | /education/videos | S11 | Tasnem | 6 | patient/family | Not Started | No
86 | P | GET | /education/relax | S11 | Tasnem | 6 | patient | Not Started | No
87 | P | GET | /patients/{serial}/care-points | S11 | Tasnem | 6 | owner | Not Started | No
88 | P | POST | /admin/users | S12 | Mohamed | 8 | admin | Not Started | No
89 | + | GET | /admin/users | S12 | Mohamed | 8 | admin | Not Started | No
90 | P | PATCH | /admin/users/{id}/role | S12 | Mohamed | 8 | admin | Not Started | No
91 | + | GET/PUT | /admin/permissions | S12 | Mohamed | 8 | admin | Not Started | No
92 | + | GET | /admin/audit | S12 | Mohamed | 8 | admin | Not Started | No
93 | + | GET | /admin/integrations | S12 | Mohamed | 8 | admin | Not Started | No
94 | + | GET | /admin/ai-models | S12 | Mohamed | 8 | admin | Not Started | No
95 | P | GET | /reports/kpis | S12 | Mohamed | 8 | director/quality | Not Started | No
96 | P | GET | /reports/monthly | S12 | Mohamed | 8 | director | Not Started | No
97 | P | GET | /nav/map | S12 | Mohamed | 9 | public | Not Started | No
98 | P | GET | /nav/search | S12 | Mohamed | 9 | public | Not Started | No
99 | P | GET | /nav/route | S12 | Mohamed | 9 | public | Not Started | No

## Mobile_Screens
# | Screen | Owner | APIs required | UI Built (prototype) | Wired to API | Languages AR/EN/RU | Status | Notes
1 | Intro slides | Mena | GET /public/hospital (optional) | Yes | No | EN only | Not Started
2 | Login (password / QR / guest) | Mena | POST /auth/login · /auth/login/qr | Yes | No | EN only | Not Started
3 | Register (modal) | Mena | POST /patients/register | Partial | No | EN only | Not Started
4 | Home (vitals, status, quick actions) | Mena | GET /patients/{serial} · GET /visits?open · GET /visits/{id}/vitals · GET /notifications | Yes | No | EN only | Not Started
5 | Care Journey — active + rating | Mena | GET /visits/{id} · POST /stages/{id}/feedback | Yes | No | EN only | Not Started
6 | Care Journey — completed visits | Mena | GET /patients/{serial}/file | Yes | No | EN only | Not Started
7 | Care & Medication | Mena | GET /visits/{id}/prescriptions · POST /prescriptions/{id}/administer | Yes | No | EN only | Not Started
8 | Appointments | Mena | GET/POST /appointments · slots · reschedule · cancel | Partial | No | EN only | Not Started
9 | Reports — health | Heba | GET /visits/{id}/results · GET /patients/{serial}/file | Yes | No | EN only | Not Started
10 | Reports — financial + pay | Heba | GET /visits/{id}/financial-file · POST /visits/{id}/payments | Partial | No | EN only | Not Started
11 | Healthcare Advisor (AI) | Heba | POST /assistant/ask · POST /assistant/triage | Partial | No | EN only | Not Started
12 | Family Access | Heba | POST/GET family · PATCH permissions · DELETE · accept · consents respond | Yes | No | EN only | Not Started
13 | Alerts | Heba | GET /notifications · POST /notifications/{id}/read | Yes | No | EN only | Not Started
14 | Learn & Relax + Care Points | Heba | GET /education/videos · /relax · care-points | Yes | No | EN only | Not Started
15 | SOS + Preferences + Accessibility | Heba | POST /emergency/sos · PUT preferences · GET/PUT accessibility | Partial | No | EN only | Not Started
16 | Indoor Map (P2) | Heba | GET /nav/map · /nav/search · /nav/route | No | No | EN only | Not Started

## Web_Dashboards
Dashboard | Route | Owner | APIs required | Priority | UI Built | Wired to API | Status | Notes
Reception | overview | Sara | GET /visits?stage=arrival · GET /appointments?status=pending | P0 | Yes | No | Not Started
Reception | register | Sara | POST /patients/register · GET insurance · POST cards · POST qr · POST /visits | P0 | Yes | No | Not Started
Reception | queue | Sara | GET /visits?filters · POST /visits/{id}/advance | P0 | Yes | No | Not Started
Reception | appointments | Sara | GET /appointments · PATCH status · POST assign · GET slots | P2 | Yes | No | Not Started
Reception | committee | Sara | POST committee-review · GET /visits?committee=pending · POST /committee/{id}/authorize | P0 | Yes | No | Not Started
Reception | billing | Sara | GET financial-file · POST payments · PATCH insurance | P2 | Yes | No | Not Started
Nurse | ward | Sara | GET /visits?dept&admitted (embeds vitals+NEWS2) | P0 | Yes | No | Not Started
Nurse | triage | Sara | GET /visits?stage=triage · POST /visits/{id}/triage | P0 | Yes | No | Not Started
Nurse | vitals | Sara | POST/GET /visits/{id}/vitals · GET risk-score | P0 | Yes | No | Not Started
Nurse | mar | Sara | GET prescriptions(due) · POST administer · GET pharmacy/availability | P0 | Yes | No | Not Started
Nurse | handover | Sara | GET /visits?dept summary (SBAR client-side) | P1 | Yes | No | Not Started
Nurse | risk | Sara | GET /visits?critical=1 · PUT thresholds · POST transport · POST checklists | P0 | Yes | No | Not Started
Doctor | worklist | Sara | GET /visits?doctor=me | P0 | Yes | No | Not Started
Doctor | file | Sara | GET /patients/{serial}/file | P0 | Yes | No | Not Started
Doctor | diagnosis | Sara | POST /visits/{id}/diagnosis | P0 | Yes | No | Not Started
Doctor | orders | Sara | POST/GET orders · POST consultations | P0 | Yes | No | Not Started
Doctor | results | Sara | GET results · POST /orders/{id}/result | P0 | Yes | No | Not Started
Doctor | prescribe | Sara | POST prescriptions · POST reconciliation · GET pharmacy | P0 | Yes | No | Not Started
Doctor | ai console | Sara | POST documentation/draft · approve · transcribe · translate | P1 | Yes | No | Not Started
Doctor | journey | Sara | POST advance · cath-type · consents · care-plan · committee | P0 | Yes | No | Not Started
Quality | overview | Sara | GET /quality/dashboard | P1 | Yes | No | Not Started
Quality | feedback | Sara | GET /feedback | P1 | Yes | No | Not Started
Quality | complaints | Sara | GET /complaints · PATCH /complaints/{id} | P1 | Yes | No | Not Started
Quality | departments | Sara | GET /quality/dashboard?by=department · PATCH route | P1 | Yes | No | Not Started
Quality | reports | Sara | GET /reports/monthly + sentiment in dashboard | P1 | Yes | No | Not Started
Admin | overview KPIs | Sara | GET /reports/kpis | P2 | Yes | No | Not Started
Admin | reports | Sara | GET /reports/monthly | P2 | Yes | No | Not Started
Admin | aimodels | Sara | GET /admin/ai-models | P2 | Yes | No | Not Started
Admin | users | Sara | GET/POST /admin/users · PATCH role | P2 | Yes | No | Not Started
Admin | permissions | Sara | GET/PUT /admin/permissions | P2 | Yes | No | Not Started
Admin | audit | Sara | GET /admin/audit | P2 | Yes | No | Not Started
Admin | integration | Sara | GET /admin/integrations | P2 | Yes | No | Not Started
Emergency | board | Sara | GET /emergency/active · POST answer · POST advance · POST code-blue | P0 | Yes | No | Not Started
Emergency | critical | Sara | GET /visits?critical=1 | P0 | Yes | No | Not Started
Emergency | metrics | Sara | GET /emergency/metrics | P1 | Yes | No | Not Started
Emergency | rules | Sara | static config | P1 | Yes | No | Not Started
Family | status | Sara | GET /visits/{id} (family resource) · POST /emergency/sos | P1 | Yes | No | Not Started
Family | updates | Sara | GET /notifications | P1 | Yes | No | Not Started
Family | team | Sara | GET /visits/{id} care-team block | P1 | Yes | No | Not Started
Family | education | Sara | GET /education/videos?stage= | P1 | Yes | No | Not Started
Family | permissions | Sara | GET /patients/{serial}/family | P1 | Yes | No | Not Started